| HIGH LIFE HIGHLAND REPORT TO THE BOARD OF DIRECTORS 29 March 2012 | AGENDA ITEM 6 REPORT No HLH 2/12 |
| --- | --- |

## FINANCE REPORT - REVENUE BUDGET 2011/12 – FINANCIAL PERFORMANCE - Report by Chief Executive

| ## Summary This report provides Directors with an update on the financial performance of High Life Highland and its Trading Company for the six months ended 31 March 2012. Directors are asked to note that :- - the forecast underspend to 31 March 2012 is £122K and that this amount will initiate the company’s reserves; and - the contract for the provision of retail sales services has been awarded to SRS Leisure Ltd. |  |  |
| --- | --- | --- |
|  | 1. 1.1 1.2 | Background The Board of High Life Highland (HLH) receives a Finance Report on a quarterly basis. A primary purpose of that report is to summarise the financial performance of the organisation and its subsidiaries. It was reported to the Board at its meeting on 8 December 2011 that there would be a forecast underspend for the period to 31 March 2012 of £111K. This forecast was based on actual results for the month of October. |
|  | 2. 2.1 2.2 2.3 2.4 2.5 2.6 | Financial Performance to 31 March 2012 A revised forecast to 31 March 2012 has been prepared incorporating actual results up to 31 December 2011. The forecast shows a net underspend for the 6 months to 31 March 2012 of £122K, an increase in the underspend of £11K from the previous forecast. Appendices A and B show the breakdown of the forecast split by function and cost type. The principal areas of underspend by business area are; - Adult and Youth, £102K - Libraries, £18K - Sports Development, £29K - Management Fees, £36K Adult and Youth is forecast to underspend by £54K in staff costs, mainly driven by lack of spend on auxiliary or sessional staff. The main area of underspend in Libraries is also in staff costs, £55K. The shortfall is due to a smaller than anticipated level of costs for relief staff, partly due to The Highland Council (THC) taking a higher than anticipated cost for October payroll costs covering work performed prior to the changeover to HLH. The overall underspend is reduced by additional expenditure related to the e-book programme launch. The main contributor to the underspend for Sports Development is miscellaneous expenditure at £26K. The Management Fees category is forecast to underspend by £36K. This is due to the amount of irrecoverable VAT being lower than budgeted. The budgeted amount of £70K for the first 6 months of operation of HLH was based on the VAT analysis prepared by KPMG as part of the business case for creating the company. Subsequent analysis revealed that the business case assumed that utility costs, subject to VAT at 20%, would remain with HLH. As these utility costs remained with THC HLH’s rate of recovery of VAT has improved from the budgeted rate of 83.1% to 88%. |
|  | 3. 3.1 | Tenders Approved / Contracts Awarded On 5 December 2011, the tender for the provision of retail sales services (at leisure centres) was awarded to SRS Leisure ltd. The contract runs until December 2013. The contract includes the provision of an on-line sales facility. |
| ### Recommendation Directors are asked to note that :- - the forecast underspend to 31 March 2012 is £122K and that this amount will initiate the company’s reserves; and - the contract for the provision of retail sales services has been awarded to SRS Leisure Ltd. |  |  |

Signature:

Designation:	Chief Executive

Date:		19 March 2012

Appendix A

HIGH LIFE HIGHLAND FORECAST  OUT-TURN TO 31 MARCH 2012

SUMMARY BY BUSINESS AREA

Row Labels

Annual

Budget

Actual Spend

to Date

Variance to

Date

Year End

Outturn

Year End

Variance

Adult & Youth

1,634,312

525,215

(253,068)

1,532,705

(101,607)

Culture

721,588

340,562

(67,018)

743,228

21,640

Facilities

937,850

457,653

(45,894)

965,996

28,146

Libraries

2,104,031

834,633

(234,097)

2,085,203

(18,828)

Sports Development

956,224

382,269

(98,760)

927,110

(29,114)

Management & Admin

652,145

303,378

21,155

665,551

13,406

Mgt Fees

(7,006,150)

0

3,503,075

(7,042,050)

(35,900)

Grand Total

0

2,843,710

2,825,393

(122,257)

(122,257)

HIGH LIFE HIGHLAND FORECAST  OUT-TURN TO 31 MARCH 2012

BY BUSINESS AREA

Values

Business Area

Split

Annual

Budget

Actual Spend

to Date

Variance to

Date

Forecast

Outturn

Forecast

Variance

Adult & Youth

Staff Costs

1,235,624

548,495

(60,556)

1,181,702

(53,922)

Other Costs

641,370

105,494

(48,374)

617,453

(23,917)

Revenues

(242,682)

(128,773)

(144,137)

(266,451)

(23,769)

Adult & Youth Total

1,634,312

525,215

(253,068)

1,532,705

(101,607)

Culture

Staff Costs

685,736

317,794

(75,074)

652,230

(33,506)

Other Costs

184,717

55,382

(34,298)

222,521

37,804

Revenues

(148,865)

(32,615)

42,353

(131,522)

17,343

Culture Total

721,588

340,562

(67,018)

743,228

21,640

Facilities

Staff Costs

2,556,419

1,114,784

(276,303)

2,553,396

(3,023)

Other Costs

105,171

118,929

114,183

132,892

27,721

Revenues

(1,723,740)

(776,059)

116,226

(1,720,292)

3,448

Facilities Total

937,850

457,653

(45,894)

965,996

28,146

Libraries

Staff Costs

1,522,332

697,198

(87,302)

1,467,521

(54,811)

Other Costs

615,463

142,514

(173,261)

645,307

29,844

Revenues

(33,764)

(5,079)

26,466

(27,625)

6,139

Libraries Total

2,104,031

834,633

(234,097)

2,085,203

(18,828)

Sports Development

Staff Costs

823,250

367,702

(43,806)

820,080

(3,170)

Other Costs

201,331

23,860

(75,661)

162,440

(38,891)

Revenues

(68,357)

(9,293)

20,707

(55,410)

12,947

Sports Development Total

956,224

382,269

(98,760)

927,110

(29,114)

Management & Admin

Staff Costs

490,387

249,214

25,423

498,769

8,382

Other Costs

161,758

54,164

(4,268)

166,782

5,024

Management & Admin Total

652,145

303,378

21,155

665,551

13,406

Mgt Fees

Other Costs

903,044

0

(451,522)

867,144

(35,900)

Revenues

(7,909,194)

0

3,954,597

(7,909,194)

0

Mgt Fees Total

(7,006,150)

0

3,503,075

(7,042,050)

(35,900)

Grand Total

0

2,843,710

2,825,393

(122,257)

(122,257)

Appendix B