Work Streams																	Appendix 7

| Section | Work Stream | Progress | Start Date | End Date | Lead | RAG |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Services | 1.1 Service Delivery Contract | Deliver PSO services required by Highland Council as detailed in the SDC schedule | October | March | All | G |
|  | 1.2 Council Elected Member engagement | Establish a “contact process” for Council Elected Members to enable the monitoring of responses to local issues | October | October | IRM | G |
|  | 1.3 Service delivery reporting | Report on PSO service delivery and performance as required by agreement in the SDC | October | March | DW | G |
| 2. Staff | 2.1 Transfer list | Manage any issues arising from the staff transfer process | October | November | GW | G |
|  | 2.2 Business support | Implement HLH staff structure and recruit staff to vacant posts | October | November | GW | G |
|  | 2.3 Staff consultation | Update schedule for staff consultations Organise series of staff inductions to HLH Update FAQs about HLH and issue | October January October | October March October | IRM IRM IRM | G G G |
|  | 2.4 Union consultation | Update schedules of meetings with full time union officials. Meeting with staff representatives. | October October | October March | GW/IRM IRM | G G |

| 3. Facilities | 3.1 Property maintenance | Issue and implement Property Maintenance Guide Establish review group Issue final version of property guide | October October March | October October March | GW GW GW | G G G |
| --- | --- | --- | --- | --- | --- | --- |
|  | 3.2 Responsible Premises Officers | Arrange training for staff to undertake this role Establish escalation process for maintenance issues | October October | October October | GW GW | G G |
|  | 3.3 Arrangements with schools | Embed new working relationships with Head Teachers | October | March | All | G |
|  | 3.4 Capital programme | Work with ECS and HaPS to deliver HLH capital projects Devise Capital Plan for 2014-2017 | October October | March March | GW All | G G |
| 4. Non property assets | 4.1 Collections Agreement | Deliver responsibilities detailed in the Collections Agreement | October | March | DW | G |
|  | 4.2 Intellectual property | Review and revise use of High Life by third parties | October | March | FH | G |
| 5. Budgets | 5.1 Budget – Oct to March 2012 | Set and deliver budget targets | October | March | All | G |
|  | 5.2 Budget – 2012/13 | Work with Finance to devise a detailed budget for HLH for the first full year of operation. Agree the proposed Services Fee to HLH. | October February | March March | IM/GW IM/GW | G G |
|  | 5.3 External audit | Implement and review audit procedures | October | March | All | G |
|  | 5.4 NNDR | Claim NNDR rates relief | October | October | GW | G |
|  | 5.5 VAT | Manage VAT claims | October | March | GW | G |
|  | 5.6 Tax | Manage Corporation Tax issues | October | March | GW | G |
| 6. Support services | 6.1 Finance | Review the options for the financial management system to be adopted by HLH Review the options for the payroll function required by HLH Select the preferred options and establish the costs Identify any training required to implement the new systems Issue tenders through procurement as required to source support to provide externally Review the tenders and select a contractor to nominate to the Board Plan the changeover to the new systems with Finance staff Arrange the transfer of staff to new payroll by April 2012 | October October December January January February October January | December December January January January February February March | All All All All GW All GW GW | G G G G G G G G |
|  | 6.2 Legal / Corporate | Select the contractors Implement the specification for the provision of specialist legal advice to HLH | October October | October October | IRM IRM | G G |
|  | 6.3 Personnel | Appoint Personnel Manager | October | November | GW | G |
|  | 6.4 Internal audit | Implement the financial management system to be operated by HLH Agree the schedule of Internal Audits by Council staff | October October | October October | GW GW | G G |
|  | 6.5 ICT | Monitor the working of the ICT contract with Fujitsu | October | March | All | G |
|  | 6.6 Grounds Maintenance | Monitor the working of the grounds maintenance contract | October | March | GW | G |
|  | 6.7 Vehicles | Monitor the working of the vehicles agreement | October | March | GW | G |
|  | 6.8 Refuse Collection | Monitor the working of the refuse agreement | October | March | GW | G |
|  | 6.9 Catering and Cleaning | Monitor the working of the catering and cleaning agreement | October | March | GW | G |
|  | 6.10 Marketing and PR | Develop proposals for the brand identity of HLH for consideration by the Board Devise proposals for the development of the company website Develop and implement the branding and marketing plan for HLH | October October October | October October March | FH FH FH | G G G |
|  | 6.11 Licenses | Ensure that PRS and Entertainment licences are in place where required | October | October | FH | G |
|  | 6.12 Education, Culture and Sport | Implement ongoing communication channels with ECS service, outwith the corporate governance process. | October | March | IRM | G |
| 7. Company matters | 7.1 HLH Board cycle | Implement Board meeting cycle | October | March | IRM | G |
|  | 7.2 Finance and Audit Committee | Establish Finance and Audit Committee. | October | October | IRM/GW | G |
|  | 7.3 Incorporation | Implement reporting to Companies House | March | March | IRM/GW | G |
|  | 7.4 Stakeholder / advisory groups | Identify a potential list of stakeholder / advisory groups to HLH. Confirm with Board of Directors Seek nominations for groups from communities of interest for each group. | October December January | November January March | IRM IRM IRM | G G G |

| 8. Risk | 8.1 Risk register | Maintain and review risk register | October | March | IRM | G |
| --- | --- | --- | --- | --- | --- | --- |
|  | 8.2 Risk management plan | Implement risk management plan to mitigate any risks rising above the line | October | March | IRM | G |
| 9. National partnerships | 9.1 National Partnerships | Meet with national agencies listed below to discuss future partnership options Scottish Government Sportscotland Creative Scotland EventScotland NHS MGS SLIC VOCAL LTS National Archives GROS HMIE Duke of Edinburgh | October | March | IRM | G |