Work Streams																	Appendix 7

| Section | Work Stream | Progress | Start Date | End Date | Lead | RAG |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Services | 1.1 Service Delivery Contract | - Deliver PSO services required by Highland Council as detailed in the SDC schedule | October | March | All | G |
|  | 1.2 Council Elected Member engagement | - Establish a “contact process” for Council Elected Members to enable the monitoring of responses to local issues | October | October | IRM | G |
|  | 1.3 Service delivery reporting | - Report on PSO service delivery and performance as required by agreement in the SDC | October | March | DW | G |
| 2. Staff | 2.1 Transfer list | - Manage any issues arising from the staff transfer process | October | November | GW | G |
|  | 2.2 Business support | - Implement HLH staff structure and recruit staff to vacant posts | October | November | GW | G |
|  | 2.3 Staff consultation | - Update schedule for staff consultations - Organise series of staff inductions to HLH - Update FAQs about HLH and issue | October January October | October March October | IRM IRM IRM | G G G |
|  | 2.4 Union consultation | - Update schedules of meetings with full time union officials. - Meeting with staff representatives. | October October | October March | GW/IRM IRM | G G |

| 3. Facilities | 3.1 Property maintenance | - Issue and implement Property Maintenance Guide - Establish review group - Issue final version of property guide | October October March | October October March | GW GW GW | G G G |
| --- | --- | --- | --- | --- | --- | --- |
|  | 3.2 Responsible Premises Officers | - Arrange training for staff to undertake this role - Establish escalation process for maintenance issues | October October | October October | GW GW | G G |
|  | 3.3 Arrangements with schools | - Embed new working relationships with Head Teachers | October | March | All | G |
|  | 3.4 Capital programme | - Work with ECS and HaPS to deliver HLH capital projects - Devise Capital Plan for 2014-2017 | October October | March March | GW All | G G |
| 4. Non property assets | 4.1 Collections Agreement | - Deliver responsibilities detailed in the Collections Agreement | October | March | DW | G |
|  | 4.2 Intellectual property | - Review and revise use of High Life by third parties | October | March | FH | G |
| 5. Budgets | 5.1 Budget – Oct to March 2012 | - Set and deliver budget targets | October | March | All | G |
|  | 5.2 Budget – 2012/13 | - Work with Finance to devise a detailed budget for HLH for the first full year of operation. - Agree the proposed Services Fee to HLH. | October February | March March | IM/GW IM/GW | G G |
|  | 5.3 External audit | - Implement and review audit procedures | October | March | All | G |
|  | 5.4 NNDR | - Claim NNDR rates relief | October | October | GW | G |
|  | 5.5 VAT | - Manage VAT claims | October | March | GW | G |
|  | 5.6 Tax | - Manage Corporation Tax issues | October | March | GW | G |
| 6. Support services | 6.1 Finance | - Review the options for the financial management system to be adopted by HLH - Review the options for the payroll function required by HLH - Select the preferred options and establish the costs - Identify any training required to implement the new systems - Issue tenders through procurement as required to source support to provide externally - Review the tenders and select a contractor to nominate to the Board - Plan the changeover to the new systems with Finance staff - Arrange the transfer of staff to new payroll by April 2012 | October October December January January February October January | December December January January January February February March | All All All All GW All GW GW | G G G G G G G G |
|  | 6.2 Legal / Corporate | - Select the contractors - Implement the specification for the provision of specialist legal advice to HLH | October October | October October | IRM IRM | G G |
|  | 6.3 Personnel | - Appoint Personnel Manager | October | November | GW | G |
|  | 6.4 Internal audit | - Implement the financial management system to be operated by HLH - Agree the schedule of Internal Audits by Council staff | October October | October October | GW GW | G G |
|  | 6.5 ICT | - Monitor the working of the ICT contract with Fujitsu | October | March | All | G |
|  | 6.6 Grounds Maintenance | - Monitor the working of the grounds maintenance contract | October | March | GW | G |
|  | 6.7 Vehicles | - Monitor the working of the vehicles agreement | October | March | GW | G |
|  | 6.8 Refuse Collection | - Monitor the working of the refuse agreement | October | March | GW | G |
|  | 6.9 Catering and Cleaning | - Monitor the working of the catering and cleaning agreement | October | March | GW | G |
|  | 6.10 Marketing and PR | - Develop proposals for the brand identity of HLH for consideration by the Board - Devise proposals for the development of the company website - Develop and implement the branding and marketing plan for HLH | October October October | October October March | FH FH FH | G G G |
|  | 6.11 Licenses | - Ensure that PRS and Entertainment licences are in place where required | October | October | FH | G |
|  | 6.12 Education, Culture and Sport | - Implement ongoing communication channels with ECS service, outwith the corporate governance process. | October | March | IRM | G |
| 7. Company matters | 7.1 HLH Board cycle | - Implement Board meeting cycle | October | March | IRM | G |
|  | 7.2 Finance and Audit Committee | - Establish Finance and Audit Committee. | October | October | IRM/GW | G |
|  | 7.3 Incorporation | - Implement reporting to Companies House | March | March | IRM/GW | G |
|  | 7.4 Stakeholder / advisory groups | - Identify a potential list of stakeholder / advisory groups to HLH. - Confirm with Board of Directors - Seek nominations for groups from communities of interest for each group. | October December January | November January March | IRM IRM IRM | G G G |

| 8. Risk | 8.1 Risk register | - Maintain and review risk register | October | March | IRM | G |
| --- | --- | --- | --- | --- | --- | --- |
|  | 8.2 Risk management plan | - Implement risk management plan to mitigate any risks rising above the line | October | March | IRM | G |
| 9. National partnerships | 9.1 National Partnerships | - Meet with national agencies listed below to discuss future partnership options - Scottish Government - Sportscotland - Creative Scotland - EventScotland - NHS - MGS - SLIC - VOCAL - LTS - National Archives - GROS - HMIE - Duke of Edinburgh | October | March | IRM | G |