| # HIGH LIFE HIGHLAND 22 September 2011 REPORT TO BOARD OF DIRECTORS | AGENDA ITEM REPORT No HLH 9/11 |
| --- | --- |

Timescale for Approval of Key Policies

### Report by Head of Community Learning and Leisure

## Summary The purpose of this report is to detail the timescale and programme for approval of key policies that High Life Highland will require to operate.

| 1. | Background |
| --- | --- |
| 1.1 | High Life Highland (HLH) requires a number of key policies under which to operate. During the transfer process, the company will work to existing Highland Council policies and the proposed timetable for changing these to HLH policies is appended. |
| 2. | Personnel Policies |
| 2.1 | Details of key personnel policies are attached at Appendix 1. These have been prioritised and will be presented to future Board meetings as detailed, for approval. Other personnel related policies will be developed and implemented by managers as necessary. |
| 3. | Finance Policies |
| 3.1 | Details of the key finance policies are attached at Appendix 2. These policies will be developed as a complete package and will be presented to Directors for approval at the March 2012 meeting. |
| ### Recommendation It is recommended that Directors: - Note the proposed timescale and programme for approval of key policies - In the meantime, note the use of existing Highland Council policies and, - Note that managers will develop and implement other personnel policies as necessary. |  |

Signature:

Designation:		Head of Community Learning and Leisure

Date:			13 September 2011

APPENDIX 1

PERSONNEL POLICIES

| Policy | For Board approval |
| --- | --- |
| Health and Safety | October 2011 |
| Code of Conduct for Employees | October 2011 |
| Disciplinary Procedure | December 2011 |
| Grievance | December 2011 |
| Harassment at Work | December 2011 |
| Whistle blowing | December 2011 |
| Equal Opportunities Policy | December 2011 |
| Early Retirement/Voluntary Severance Scheme | June 2012 |
| Employee Death in Service | June 2012 |
| Employee Development Strategy | June 2012 |

APPENDIX 2

FINANCE POLICIES

| Policy | To be completed by |
| --- | --- |

Financial Regulations 				March 2012

  - Scope & Responsibilities

  - Financial Management & Reporting

  - Financial Governance

Contract Standing Orders

  - Context

  - Applicable Standards

  - Operational Procedures

Scheme of Delegation

Information Systems Security Policy

Risk Management Strategy