| HIGH LIFE HIGHLAND REPORT TO BOARD OF DIRECTORS 6 December 2012 | AGENDA ITEM 10 REPORT No HLH 35/12 |
| --- | --- |

## Quarterly Performance Report - Report by Chief Executive

Summary The purpose of this report is to present performance information for the period of July to October 2012. It is recommended Directors note that seven out of the ten high level agreed performance indicators have been rated as being on target, with three not yet having been assessed because they are annual indicators.

| 1. | Background |
| --- | --- |
| 1.1 | At the September 2012 meeting Directors agreed that its high level performance monitoring should focus on ten business critical areas. |
| 1.2 | Appendix A contains the summary of performance against the ten performance indicators. Appendices B to D contain further information on the indicators. |
| 2. | Business Plan Contribution |
| 2.1 | This report will assist the Board in monitoring performance against all of the business outcomes in the Business Plan and will provide the board with an overview of the performance of the organisation. |
| 3. | Summary of performance |
| 3.1 | Seven out of the ten indicators have been rated as being on target. Three have not been assessed because they are annual indicators. |
| 4. | Risk |
| 4.1 | There are no new risks identified as a result of the production of this report. |
| Recommendation It is recommended Directors note that seven out of the ten high level ageed performance indicators have been rated as being on target, with three not yet having been assessed because they are annual indicators. |

Signature:

Designation:	Chief Executive

Date:		22 November 2012

Business Critical Indicators - Summary													Appendix A

| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating November 2012 | Summary of Performance: November 2012 |
| --- | --- | --- | --- | --- |
| High level relationship with THC | Annual | Annual meeting, with one of the agenda items to be “assessment of the relationship between HLH and THC”, between: the HLH chair, vice chair and the chair of the HLH Finance and Audit Committee; and THC’s Leader and Budget Leader | - | Not required until March 2013 |
| Delivery of the SDC with THC | Twice per year | Agreement of THC’s Culture and Leisure Contracts Scrutiny Sub-Committee that HLH has met the terms of the SDC. | G | At its meeting held on 26 September 2012, THC’s Culture and Leisure Contracts Scrutiny Sub-Committee noted that HLH had met or exceeded the terms of the SDC during October to March 2011/12. The next review of performance of the SDC by the sub-committee is scheduled for its meeting in February 2013 which will assess performance for the three quarters during April to December 2012. |
| Delivery of business plan objectives | Quarterly | Reporting all actions which have been RAG rated red with reasons (and remedial action if appropriate). | G | The overall rating for performance against the business plan has being assessed as being on target. The list of actions which are red along with explanations/corrective action is in Appendix B. Of the 312 operational plan actions: 10 are complete 241 are green 19 are amber 42 are red (13 of these are recommended for removal) |
| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating November 2012 | Summary of Performance: November 2012 |
| Financial monitoring | Quarterly | Financial monitoring reports. It is suggested that this be RAG rated (Red/Amber/Green) where: Red = Delivery of SDC over budget Amber = Delivery of SDC on budget Green = Delivery of SDC within budget | G | As detailed in the finance report , it is projected that the Service Delivery Contract will be delivered within budget. |
| Health and safety | Annual/ Quarterly | Annual external assessment and report which is agreed by the HLH board. Quarterly review of RIDDOR reportable accidents/incidents. | G | The board will receive an annual health and safety report at its meeting scheduled for 6 December 2012. |
| Risk management | Annual | Annual risk report agreed by the HLH board. (The risk register is reviewed quarterly by the finance and audit committee) | G | The risk register scheduled for review by the board in March 2013. The Finance and Audit Committee has considered the risk register quarterly. |
| Leisure centre customer numbers | Quarterly | Comparison graph or trend analysis to the same period in the preceding year(s). | G | Customer numbers at High Life sites have increased as can be seen in Appendix C. |
| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating November 2012 | Summary of Performance: November 2012 |
| Quality of service provision | Annual | Annual board report on: Internal assessment of quality: customer survey for each of the nine areas of work. review of comments and complaints External assessments of quality e.g.: THC’s annual public performance survey. Museum Accreditation (takes place every five years) The Public Library Quality Improvement Matrix HMIe inspection of Community Learning and Development | G | The Council’s public performance survey is carried out annually by the University of the Highlands and Islands. Further background information on the survey can be seen in the report considered by the board on 20 October 2011 Report No. HLH21/11. As can be seen in Appendix D, user satisfaction has gone down in 2011 compared with 2012 for two services and has increased for three. In terms of rankings, one has remained the same with two increasing and two decreasing. The overall trend of the net satisfaction rate is positive as can be seen in the graph in appendix D. There are a number of other ways of assessing service quality either in existence or being developed nationally. The senior management team will assess fitness for purpose for the schemes being developed and adopt them if they are useful. These will be the subject of a future board repost. |
| Staff satisfaction | Annual | Annual staff survey and report to the HLH board which includes a year on year comparison of the overall rating of staff satisfaction. | - | The first staff survey is scheduled to be complete in March 2013 and there will be a report for consideration by the Board at its June 2013 meeting. |
| Value for money | Annual | There are three areas of work which can be benchmarked nationally (and year on year) for value for money by calculating the cost per attendance. These are: Leisure Facilities; Libraries; and Museums. | - | Reporting on value for money is scheduled for March 2013 when CIPFA (Chartered Institute of Public Finance Accountants) figures for 2011/12 have been published and available for comparison with financial year 2010/11. (CIPFA stats are published in January each year). |

*RAG

Red 	= No Significant Progress

Amber = Some Slippage

Green = On Target

Operational Plan RAG Rating as at end October 2012											Appendix B

| Service Area | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| --- | --- | --- | --- |
| Corporate | Implement a Property Asset Management Strategy for HLH, including developing a 5 year capital programme with Highland Council | Dec 2012 | THC has yet to set its capital programme and deadlines for bidding/projects. Recommended revise deadline to: “keep under review pending THC capital plan development” |
|  | Develop an ICT Strategy for HLH | Dec 2013 | THC has yet to reach a decision on whether to continue with its existing ICT infrastructure “Pathfinder”. If it chooses to retain Pathfinder, HLH establishing its own ICT system will be cost prohibitive. Recommended revise deadline to: “keep under review pending THC decision on Pathfinder” |
| Adult Learning | None |  |  |
| Archives | None |  |  |
| Arts | None |  |  |
| Leisure Facilities | Actively promote and cross-sell other HLH services to customers | Ongoing | Build into marketing plan scheduled for completion - August 2013 |
|  | Develop content for promotional HLH videos for screening in facility receptions. | Aug 2012 | Will follow as a later priority with the Marketing and communications plan. Revised target date – August 2013 |
|  | Implement and manage the new HLH customer feedback and customer complaints system | Aug 2012 | Will be developed within the revised Marketing and Communications plan target date – March 2013. |
|  | Agree the criteria for HLH sponsorship of a third party | October 2012 | This target is dependent on feedback from the Sponsorship and Funding Committee. Revised target date – March 2013. |
|  | Devise the business case to consider adding High Life sales staff to the establishment | Oct 2012 | Will be considered once the core staffing establishment of each facility is agreed and recruited. Revised target date – October 2013 |
| Service Area | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| Leisure Facilities (cont’d) | Develop the business case to consider the option to establish the role of Programme Manager to review the services provided across HLH and to maximise on cross service collaboration | Oct 2012 | As above, will be considered once the core staffing establishment of each facility is agreed and recruited. Revised target date – October 2013 |
|  | Review the opportunities to introduce cultural services into leisure facilities and vice versa | Oct 2012 | Will follow on from the review of existing leisure programmes. Revised target date – October 2013 |
|  | Undertake review of the Learn to Swim Programme to maximise on accessibility and uptake – scheduled for implementation March 3013. | August 2012 | Recommended removal from operational plan. Duplication with previous action in business outcome 1: “Develop and deliver the Highland Learn to Swim programme” |
|  | Establish and hold a stock of consumable parts to carry out internal repairs of leisure equipment | Oct 2012 | Recommended removal from operational plan – not feasible because of contractual arrangements |
|  | Scrutinise the ongoing maintenance programme with HaPS to ensure adherence to the agreed programme | Ongoing | Recommended removal from operational plan – no longer required following appointment of Principal Estates Manager. |
|  | Introduce a rolling programme of audits and maintenance of leisure equipment not covered by the HaPS programme to maintain the value of the stock | May 2012 | Recommended removal from operational plan - not feasible because of contractual arrangements. |
|  | Contribute to the introduction of a mechanism to review customer satisfaction with HLH services annually | Oct 2012 | Recommended removal from operational plan – duplicated by “Monitor, through a review of the system, that operational staff have the tools to respond positively to customer comments and to resolve complaints received” |
|  | Increase the use of email to communicate with all customers and reduce the amount of postage issued | Ongoing | Recommended removal from operational plan – duplicated from “Maximise the use of electronic communication with customers through email, social media, electronic newsletters and the introduction of phase 2 of the website” |
| Service Area | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| Leisure Facilities (cont’d) | Organise and deliver a series of Familiarisation sessions to facilitate the process of cross selling and appreciation of the value of the work of other HLH staff | Aug 2012 | Recommended removal from operational plan – overtaken by work of Principal Managers working together on joint projects. |
|  | Work with the Youth and Arts teams to develop proposals for the ‘Y Factor’ in collaboration with Northern Constabulary | Aug 2012 | Recommended removal from operational plan – overtaken by Northern Constabulary developing an alternative programme. |
| Libraries | Cascade training on retail methods and good practice in display and promotion of products to at least one member of staff in all libraries. | Annual Review | Key staff mentor on long term sick leave, now returned to work. Recommended review of progress June 2013. |
|  | Develop an E-Reader Promotion to attract new High Life Members. | Apr 2012 | Senior Management Team decision not to proceed until project ready for consideration by HLH board (decision taken following consideration of risks). New target date April 2013. |
|  | Introduce a reading group for Home Educated families, and those with literacy challenges | Mar 2013 | Actions to progress this identified that this was no longer desired/required by customer groups. Recommended that this action be removed from the operational plan. There are various other reading groups throughout the area which individuals can be directed to and staff will support reading groups where there is a community interest. |
|  | Customer care training rolled out or cascaded to all staff | Mar 2013 | Training not yet developed. Recommended revised target date of October 2013. |
|  | Sharing of customer base with internal partners to build customers in all sectors | Aug 2012 | To be developed as part of marketing plan. Revised target date August 2013 |
| Service Area | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| Libraries (cont’d) | Seek external funding stream for review of mobile library service due to start 2013 | Aug 2012 | Action complete. The two national libraries organisations have been contacted and no funding is available. It is recommended that this action be removed from the operational plan and that the review be completed internally instead of using external funding. |
| Museums | Re-tender catering at IMAG |  | Corporate decision not to proceed at this time. Action under review. |
| Outdoor Learning | Since operational plan completed, Badaguish Outdoor Centre has transferred to THC. The three actions relating to provision of adventurous activity and offsite excursions safety system are all green. |  |  |
| Sport | Roll out the incremental development of the High Life membership package – adding value across the range of HLH services at regular intervals – separate work streams document contains detail | Aug 2012 | Technological issues to be resolved prior to action being undertaken - Revised target date Aug 2013 |
|  | Profile the potential uptake and impact for HLH of the introduction of High Life Club – separate work streams document contains detail | Aug 2012 | Scoping document complete. Pilot scheduled for January to March 2013. Revised target date March 2013 |
|  | Introduce hand held card readers to be used in all facilities without HLH tills | Oct 2012 | Recommended removal from operational plan. Cheaper alternative system for customer bookings through using leisure facilities as booking sites and the development of on-line bookings. |
|  | Contribute to the introduction of a mechanism to review customer satisfaction with HLH services annually | Oct 2012 | Recommended removal from operational plan – duplicated by “Monitor, through a review of the system, that operational staff have the tools to respond positively to customer comments and to resolve complaints received” |
| Service Area | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| Sport (Cont’d) | Increase the use of email to communicate with all customers and reduce the amount of postage issued | Ongoing | Recommended removal from operational plan – duplicated from “Maximise the use of electronic communication with customers through email, social media, electronic newsletters and the introduction of phase 2 of the website” |
| Youth Work | Explore opportunities for High Life loyalty points and whether this can be integrated to the national Young Scot rewards scheme | December 2012 | This action has been overtaken by the review of High Life which will encompass an examination of potential links to other cards incentive schemes. |

Actions RAG rated red covering more than one service area

| Service Areas | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| --- | --- | --- | --- |
| Leisure Facilities; Sport | Monitor, through a review of the system, that operational staff have the tools to respond positively to customer comments and to resolve complaints received. | Ongoing | Will follow on from the introduction of the new HLH customer complaints and comments systems. To be developed as part of marketing plan – revised target date August 2013. |
|  | Agree the criteria for HLH sponsorship of a third party. | Oct 2012 | Will be addressed through the work of the Funding and Sponsorship Committee which is focusing on seeking sponsorship for HLH as an initial priority. Revised target date to be considered by Funding and Sponsorship Committee. |
|  | Establish and implement a code of conduct for leisure facility/sports staff that encourages the role model behaviour required of HLH personnel at all levels. | Aug 2012 | Dependant on action to “Roll out the staff “induction” pack explaining to all staff what HLH is, who we work for and the ambition of our company”. Revised target date April 2013 |
|  | Contribute to the process to complete and implement phase 2 of the HLH web site and launch | Jun 2012 | Update to be provided at December 2012 board meeting. Revised target date – June 2013 |
| Service Areas | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| Leisure Facilities; Sport (cont’d) | Identify opportunities to develop new services in partnership with the following organisations: Outdoor activity providers Forest Enterprise Major event organisers Northern Constabulary Highlands and Islands Fire and rescue Service Other Local Authorities Countryside Rangers Cairngorm National Park | Aug 2012 | To follow once a review of existing programmes provided by leisure facilities is complete and internal opportunities have been maximised first. Revised target date – October 2013. |
| Adult Learning; Leisure Facilities; Libraries; Sport; Youth Work | Roll out the staff “induction” pack explaining to all staff what HLH is, who we work for and the ambition of our company | Apr 2012 | First draft of the induction pack has been completed. Final version scheduled for January when it will go to Unions for consultation. Recommended revised target date April 2013. |

RAG rating definitions:

- Red = No Significant Progress

- Amber = Some Slippage

- Green = On Target

Appendix C

User numbers for facilities which offer High Life

Total user numbers 1st April – 31st October 2011 = 368478

Total user numbers 1st April – 31st October 2012 = 470369

Total Increase/decrease %                                      = +28%

This 28% increase is broken down as follows:

- 10% - Closure of Dingwall swimming pool 2011 / reopening of pool and refurbishment of fitness suite 2012

- 4% - Closure of Lochbroom swimming pool 2010.11 / reopening 2011.12

- 3% -  Increase in fitness class provision at Lochaber Leisure Centre since                          refurbishment last quarter of 2011

- 11% - General increase in fitness programmes

Appendix D

Quality Framework – Extract from the Highland Council’s Annual Survey of Performance and Attitudes 2012:

Views on The Highland Council’s Services: The Net Satisfaction Rate Service

|  | 2012 % | 2011 % | 2010 % | 2009 % | 2008 % |
| --- | --- | --- | --- | --- | --- |
| Payment of Council Tax | 83 | 82 | 78 | 72 | 72 |
| Libraries | 81 | 89 | 78 | 65 | 62 |
| Walking routes e.g. Great Glen Way | 80 | 83 | 77 | 56 | 56 |
| Council Service Points | 74 | 83 | 74 | 72 | 70 |
| Public Parks and other open spaces | 73 | 82 | 63 | 48 | 45 |
| Registrars for Births, Deaths & Marriages | 73 | 80 | 74 | 54 | 59 |
| Recycling facilities | 72 | 66 | 61 | 57 | 48 |
| Refuse/bin collection | 72 | 73 | 74 | 72 | 73 |
| Other sports facilities | 69 | 72 | 52 | 33 | 34 |
| Burials and cremations | 68 | 68 | 63 | 41 | 45 |
| Countryside ranger service | 67 | 71 | 61 | 39 | 36 |
| Primary education | 65 | 64 | 74 | 49 | 56 |
| Swimming pools | 64 | 62 | 53 | 40 | 37 |
| Street lighting | 64 | 69 | 63 | 58 | 53 |
| Museums | 64 | 79 | 59 | 35 | 36 |
| Pre-school services | 62 | 65 | 63 | 38 | 37 |
| Secondary education | 57 | 63 | 60 | 39 | 44 |
| Environmental Health Service | 55 | 53 | 33 | 23 | 23 |
| Cycling paths | 50 | 65 | 36 | 19 | 28 |
| Community learning/adult education | 47 | 41 | 32 | 20 | 26 |
| School meals | 45 | 60 | 45 | 28 | 31 |
| Street cleaning | 43 | 37 | 30 | 30 | 25 |
| Trading Standards | 41 | 42 | 38 | 19 | 20 |
| Economic development / business support | 35 | 27 | 10 | 3 | 3 |
| School transport | 33 | 45 | 51 | 31 | 33 |
| Advice on Benefits | 31 | 34 | 20 | 18 | 18 |
| Housing information and advice | 30 | 30 | 18 | 12 | 14 |
| Community Occupational Therapy | 30 | 28 | 17 | 8 | 10 |
| Services to protect adults at risk from harm | 29 | 25 | 18 | n/a | n/a |
| Services to protect children from harm | 28 | 37 | 24 | 14 | 18 |
| Breakfast and after school clubs | 24 | 46 | 28 | 7 | 11 |
| Gaelic Primary education | 24 | n/a | n/a | n/a | n/a |
| Care at home services | 23 | 25 | 23 | 14 | 10 |
| Residential homes for disabled/elderly people | 21 | 32 | 11 | 6 | 4 |
| Gaelic Pre-school services | 21 | n/a | n/a | n/a | n/a |
| Public conveniences | 19 | 38 | 18 | 1 | 4 |
| Dealing with flooding | 18 | 28 | 21 | 19 | 11 |
| Pavement maintenance | 16 | 8 | 6 | 3 | -7 |
| Gaelic community learning/adult education | 15 | n/a | n/a | n/a | n/a |
| Gaelic Secondary education | 13 | n/a | n/a | n/a | n/a |
| Planning for future land use (Local Plan) | 3 | 3 | -9 | -9 | -5 |
| Winter road maintenance | 0 | -9 | -23 | -3 | -2 |
| Planning applications and building warrants | -2 | 2 | -4 | -3 | -6 |
| Services to reduce youth offending | -13 | -9 | -27 | -27 | -27 |
| Road repairs and pot holes | -59 | -55 | -57 | -50 | -55 |

Appendix D (cont.)

Quality Framework – The Highland Council’s Annual Survey of Performance and Attitudes 2012: Net Satisfaction Rate Trends